## Transmission
From Bus | To Bus | Branch Num | Duration | Other Considerations
89 | 90 | 142 | 3 days | Materials not available until 8/16
94 | 96 | 150 | 2 weeks | Add customer tap in middle by 4/1. Add 50MW load . Line uprate to 225MVA.
83 | 85 | 131 | 1 day | Breaker PM
27 | 32 | 43 | 20 weeks | Can be broken up into 2 week sections.
25 | 27 | 33 | 3 weeks
70 | 74 | 114 | 2 days
42 | 49 | 66 | 6 weeks | Needs to overlap exactly 1 week with 67
42 | 49 | 67 | 6 weeks | Needs to overlap exactly 1 week with 66
79 | 80 | 125 | 10 days
80 | 98 | 152 | 2 weeks | Concurrent with 153
80 | 99 | 153 | 2 weeks | Concurrent with 152
77 | 80 | 123 | 4 weeks | Concurrent with 124, must be done by 7/1 for regulatory compliance
77 | 80 | 124 | 4 weeks | Concurrent with 123, must be done by 7/1 for regulatory compliance
56 | 59 | 85 | 1 week | Same crew as 86
56 | 59 | 86 | 1 week | Same crew as 85
103 | 104 | 165 | 3 weeks | Permits not available until 4/1
103 | 105 | 166 | 4 weeks | Permits not available until 4/1
104 | 105 | 168 | 3 weeks | Permits not available until 4/1
100 | 103 | 163 | 6 weeks | Permits not available until 4/1
100 | 104 | 164 | 2 weeks | Permits not available until 4/1
12 | 14 | 17 | 5 days | Must be complete by 4/1
61 | 62 | 92 | 2 weeks | Units at 61 and 62 must be offline for this work
65 | 66 | 102 | 2 days | Must be complete by 7/1 for regulatory compliance
51 | 52 | 72 | 8 weeks
52 | 53 | 73 | 8 weeks

## Generation
Bus | Pmax | Pg | Start | Duration (Weeks)
15 | 100 | 0 | 2023-03-01 | 6
26 | 414 | 414 | 2023-03-01 | 4
70 | 100 | 100 | 2023-03-01 | 2
46 | 119 | 119 | 2023-03-07 | 2
111 | 136 | 136 | 2023-03-07 | 2
69 | 805.2 | 805.2 | 2023-03-15 | 3
74 | 100 | 100 | 2023-03-15 | 2
10 | 550 | 550 | 2023-03-21 | 4
73 | 100 | 0 | 2023-04-01 | 2
100 | 352 | 352 | 2023-04-05 | 4
40 | 100 | 0 | 2023-09-01 | 8
116 | 100 | 0 | 2023-09-15 | 5
54 | 148 | 148 | 2023-10-01 | 2
80 | 577 | 577 | 2023-10-01 | 6
55 | 100 | 100 | 2023-10-15 | 2
89 | 707 | 707 | 2023-10-15 | 4
112 | 100 | 0 | 2023-10-15 | 2
56 | 100 | 100 | 2023-11-01 | 2
59 | 255 | 255 | 2023-11-15 | 2