## Schedule
Branch Num | Duration (Hours) | Other Considerations
142 | 72 | Materials not available until 8/16
150 | 336 | Add customer tap in middle by 4/1. Add 50MW load . Line uprate to 225MVA.
131 | 24 | Breaker PM
43 | 3360 | Can be broken up into 2 week sections.
33 | 504
114 | 48
66 | 1008 | Needs to overlap exactly 1 week with 67
67 | 1008 | Needs to overlap exactly 1 week with 66
125 | 240
152 | 336 | Concurrent with 153
153 | 336 | Concurrent with 152
123 | 672 | Concurrent with 124, must be done by 7/1 for regulatory compliance
124 | 672 | Concurrent with 123, must be done by 7/1 for regulatory compliance
85 | 168 | Same crew as 86
86 | 168 | Same crew as 85
165 | 504 | Permits not available until 4/1
166 | 672 | Permits not available until 4/1
168 | 504 | Permits not available until 4/1
163 | 1008 | Permits not available until 4/1
164 | 336 | Permits not available until 4/1
17 | 120 | Must be complete by 4/1
92 | 336 | Units at 61 and 62 must be offline for this work
102 | 48 | Must be complete by 7/1 for regulatory compliance
72 | 1344
73 | 1344