## Transmission
Branch Num | Duration | Split | Starting Time Frame | Ending Time Frame | Dependency | Outage Overlap | Independency | Bus Status | Load (MW) | Line Uprate (MVA) | Notes
142 | 3 days |  | 2023-08-16 | 2023-12-31 |  |  |  | ON |  |  | Materials not available until 8/16
150 | 2 weeks |  | 2023-01-01 | 2023-03-31 |  |  |  | ON | 50 | 225 | Add customer tap in middle by 4/1. Add 50MW load . Line uprate to 225MVA.
131 | 1 day |  | 2023-01-01 | 2023-12-31 |  |  |  | ON |  |  | Breaker PM
43 | 20 weeks | 2 weeks | 2023-01-01 | 2023-12-31 |  |  |  | ON |  |  | Can be broken up into 2 week sections.
33 | 3 weeks |  | 2023-01-01 | 2023-12-31 |  |  |  | ON
114 | 2 days |  | 2023-01-01 | 2023-12-31 |  |  |  | ON
66 | 6 weeks |  | 2023-01-01 | 2023-12-31 | 67 | 1 week |  | ON |  |  | Needs to overlap exactly 1 week with 67
67 | 6 weeks |  | 2023-01-01 | 2023-12-31 | 66 | 1 week |  | ON |  |  | Needs to overlap exactly 1 week with 66
125 | 10 days |  | 2023-01-01 | 2023-12-31 |  |  |  | ON
152 | 2 weeks |  | 2023-01-01 | 2023-12-31 | 153 | 2 weeks |  | ON |  |  | Concurrent with 153
153 | 2 weeks |  | 2023-01-01 | 2023-12-31 | 152 | 2 weeks |  | ON |  |  | Concurrent with 152
123 | 4 weeks |  | 2023-01-01 | 2023-06-30 | 124 | 4 weeks |  | ON |  |  | Concurrent with 124, must be done by 7/1 for regulatory compliance
124 | 4 weeks |  | 2023-01-01 | 2023-06-30 | 123 | 4 weeks |  | ON |  |  | Concurrent with 123, must be done by 7/1 for regulatory compliance
85 | 1 week |  | 2023-01-01 | 2023-12-31 |  |  | 86 | ON |  |  | Same crew as 86
86 | 1 week |  | 2023-01-01 | 2023-12-31 |  |  | 85 | ON |  |  | Same crew as 85
165 | 3 weeks |  | 2023-04-01 | 2023-12-31 |  |  |  | ON |  |  | Permits not available until 4/1
166 | 4 weeks |  | 2023-04-01 | 2023-12-31 |  |  |  | ON |  |  | Permits not available until 4/1
168 | 3 weeks |  | 2023-04-01 | 2023-12-31 |  |  |  | ON |  |  | Permits not available until 4/1
163 | 6 weeks |  | 2023-04-01 | 2023-12-31 |  |  |  | ON |  |  | Permits not available until 4/1
164 | 2 weeks |  | 2023-04-01 | 2023-12-31 |  |  |  | ON |  |  | Permits not available until 4/1
17 | 5 days |  | 2023-01-01 | 2023-03-31 |  |  |  | ON |  |  | Must be complete by 4/1
92 | 2 weeks |  | 2023-01-01 | 2023-12-31 |  |  |  | OFF |  |  | Units at 61 and 62 must be offline for this work
102 | 2 days |  | 2023-01-01 | 2023-06-30 |  |  |  | ON |  |  | Must be complete by 7/1 for regulatory compliance
72 | 8 weeks |  | 2023-01-01 | 2023-12-31 |  |  |  | ON
73 | 8 weeks |  | 2023-01-01 | 2023-12-31 |  |  |  | ON

## Generation
Bus | Pmax | Pg | Start | Duration (Weeks)
15 | 100 | 0 | 2023-03-01 | 6
26 | 414 | 414 | 2023-03-01 | 4
70 | 100 | 100 | 2023-03-01 | 2
46 | 119 | 119 | 2023-03-07 | 2
111 | 136 | 136 | 2023-03-07 | 2
69 | 805.2 | 805.2 | 2023-03-15 | 3
74 | 100 | 100 | 2023-03-15 | 2
10 | 550 | 550 | 2023-03-21 | 4
73 | 100 | 0 | 2023-04-01 | 2
100 | 352 | 352 | 2023-04-05 | 4
40 | 100 | 0 | 2023-09-01 | 8
116 | 100 | 0 | 2023-09-15 | 5
54 | 148 | 148 | 2023-10-01 | 2
80 | 577 | 577 | 2023-10-01 | 6
55 | 100 | 100 | 2023-10-15 | 2
89 | 707 | 707 | 2023-10-15 | 4
112 | 100 | 0 | 2023-10-15 | 2
56 | 100 | 100 | 2023-11-01 | 2
59 | 255 | 255 | 2023-11-15 | 2